## Sheet1
Seattle Department of Transportation
Bridging the Gap Planned Accomplishments
Year: 2010 | [5 empty] | Annual target has been met |  |  | 43 accoplishment types are green
Run Date: 01/20/2011 | [5 empty] | Annual target is on track to be met |  |  | 0 accoplishment types are light green
Division: All | [5 empty] | Annual target is on track with caution |  |  | 0 accomplishment types are yellow
Program: All | [5 empty] | Annual target will not be met |  |  | 0 accomplishment types are red
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices evaluated | Count | 225 | 68 | 78 | 60 | 46 | 252
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices installed, modified or removed | Count | 50 | 6 | 28 | 12 | 12 | 58
Commuter Mobility | Policy and Planning |  | Transit Service | Secured transit hours | Count | 14800 | 0 | 0 | 0 | 14800 | 14800
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Speed watch trailer deployed | Times | 60 | 16 | 21 | 22 | 2 | 61
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Traffic control concerns evaluated | Count | 500 | 214 | 205 | 155 | 61 | 635
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn improvements installed | Signalized Intersection | 4 | 1 | 2 | 0 | 2 | 5
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn signal improvements evaluated | Intersections | 20 | 14 | 7 | 2 | 1 | 24
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New signals installed | Count | 3 | 1 | 0 | 1 | 0 | 3
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New traffic signal requests evaluated | Count | 50 | 26 | 14 | 8 | 5 | 53
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Corridor and Intersection Improvements | Traffic Management |  | Collision Evaluation Program | Safety concerns investigated | Count | 55 | 18 | 3 | 8 | 27 | 56
Corridor and Intersection Improvements | Policy and Planning |  | Transit Corridor Projects | Transit corridor project implementation | Milestones | 3* | 0 | 0 | 0 | 3 | 3
Neighborhood Enhancements | Traffic Management |  | NSF/CRF neighborhood project implementation | Large neighborhood project implementation | Projects selected | Complete Selection | 0 | 0 | 11 | 0 | 11
Neighborhoods | Traffic Management |  | Pedestrian Master Plan - Crossing Improvments | Crossing improvements implemented | Count | 40 | 4 | 18 | 9 | 11 | 42
Neighborhoods | Traffic Management |  | Traffic Safety Programs | Locations improved for pedestrian safety | Count | 10 | 1 | 7 | 2 | 0 | 10
Neighborhoods | Traffic Management |  | Safety Programs (incl. Safe Routes to Schools) | Walking routes to schools improved for safety | Number of Schools | 5 | 0 | 1 | 4 | 0 | 5
Roads | Capital Projects and Roadway Structures |  | Arterial Asphalt and Concrete Program | Roads paved | Lane miles | 22 | 0 | 8.8 | 13.1 | 9.9 | 31.8
Sidewalk Maintenance | Street Maintenance |  | Sidewalk Safety Repair | Sidewalks repaired | Block Equivalent | 22 | 4.76 | 13.24 | 4.65 | 1.88 | 24.53
Signal Major Maintenance | Traffic Management |  | Pedestrain Countdown Signals | Pedestrain countdown signals installed | Intersections | 40 | 32 | 8 | 0 | 0 | 40
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Arterials restriped (plus edgelines) | Lane Line Miles | 1148 | 98.62 | 497.66 | 464.49 | 87.34 | 1148.11
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Crash cushions replaced | Count | 2 | 0 | 0 | 2 | 0 | 2
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Crosswalks remarked | Count | 600 | 82 | 146 | 399 | 4 | 631
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Guardrail replaced/installed | Linear feet | 1910 | 1072.5 | 120.5 | 162.5 | 667.5 | 2023
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Signs and Markings | Traffic Management |  | Sign Replacement Program | Regulatory street signs replaced | Count | 6500 | 1602 | 2083 | 2237 | 1622 | 7544
Signs and Markings | Traffic Management |  | School Zone Signage Improvements | Signage of school zone improved | Number of Schools | 10 | 6 | 2 | 2 | 0 | 10
Signs and Markings | Traffic Management |  | Sign Replacement Program | Signs replaced within a corridor | Corridors | 1 | 0 | 0 | 0 | 1 | 1
Signs and Markings | Traffic Management |  | Sign Replacement Program | Street name signs replaced | Intersections | 1700 | 481 | 331 | 352 | 537 | 1701
Structures Maintenance | Capital Projects and Roadway Structures |  | Bridge/Structure Maintenance | Bridge repair requests completed | Count | 270 - 320 | 107 | 87 | 44 | 52 | 290
Structures Maintenance | Capital Projects and Roadway Structures |  | Stairway/Structure Maintenance | Stairways rehabilitated | Count | 3 - 5 | 1 | 2 | 0 | 0 | 3
Traffic Signals | Traffic Management |  | Traffic Signals Maintenance | Signal beacon maintained | Count | 105 | 105 | 0 | 0 | 0 | 105
Traffic Signals | Traffic Management |  | Traffic Signal Operations | Traffic control cabinets replaced | Count | 7 | 1 | 2 | 7 | 0 | 10
Traffic Signals | Traffic Management |  | Traffic Signal Maintenance | Traffic signals maintained | Maintenance Events | 1040 | 130 | 667 | 204 | 39 | 1040
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Bicycle facility maintenance | Lane miles | 35 | 7.74 | 25.75 | 0.12 | 1.4 | 35.01
Trails and Bike Paths | Traffic Management |  | Bike Spot Safety Improvements | Bicycle parking (racks) | spaces | 350 | 140 | 95 | 80 | 44 | 359
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike lanes and sharrows striped | Miles | 20 | 0 | 9.43 | 4.76 | 6.04 | 20.23
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike route signs installed | Miles of bike routes | 30 | 11.99 | 0 | 13.85 | 5.7 | 31.54
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike trail segments built | Count | 1 | 1 | 0 | 0 | 0 | 1
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan - ADA Improvements | Design and coodinate construction new curb ramps | Count | 265 | 77 | 117 | 76 | 0 | 270
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan - Sidewalk Development | Sidewalks built | Block equivalent | 15 | 0.2 | 2.7 | 1 | 11.2 | 15.1
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Trail Inspection | Miles of trails | 20 | 26.72 | 0 | 0 | 0 | 26.72
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Urban trail and bikeway spot imporvements | Count | 46 | 8 | 20 | 14 | 4 | 46
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Landscape Maintenance | Landscape maintenance | Maintenance Events | 840 | 141 | 568 | 477 | 343 | 1529
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees planted | Count | 800 | 0 | 468 | 6 | 377 | 851
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees pruned | Count | 3000 | 769 | 602 | 1809 | 601 | 3781