## Transportation
Transportation and Land Use
| Action | Lead staff | Lead Dept | Other Dep'ts Involved | 2013 Implementation Tasks | 2014 Implementation Tasks | Needed Policy Decisions | Existing Resources | Needed Resources | Public Engagement | Implementation Status
TLU 1 | Renew and extend the time frame of the Bridging the Gap (BTG) levy and prioritize investments in transit, pedestrian, cycling improvements and system maintenance. | Dori | SDOT | CBO, Leg, MO | SDOT is doing background work to prepare for a major kickoff on BTG renewal in 2014. | Begin public engagement, develop funding alternatives and prepare proposed package. | City Council and the Mayor will need to determine the size, length, and contents of a transportation funding package, as well as when to put a measure on the ballot. | The 2014 proposed budget contains $350,000 to begin planning/ community involvement. | The MO also anticipates an additional investment of $300,000 in 2015. | It is likely that preparation for BTG renewal will require numerous public meetings, involvement of the BTG Oversight Committee, social media engagement, on-line surveys and focus groups. SDOT will need to engage various stakeholders and ensure it reaches out to all corners of Seattle, particularly historically underrepresented communities. | On Track. SDOT is developing a levy proposal for MO review. Once approved by the Mayor, SDOT will work with the BTG Oversight Committee in late winter/early spring 2015 to seek input on the proposal from the public and interested stakeholders. MO will review the input and finalize the proposal and then transmit to Council for their review in time for the November 2015 general election.
TLU 2 | Secure local or transit agency authority to levy a motor vehicle excise tax (MVET) at the City or County level. | Dori/Cheryl | OIR | Leg, MO | Develop updated legislative agenda for 2014 with Office of Intergovernmental Relations (OIR), which will include a transportation funding package. Monitor activities at State level, particularly potential December 2013 special session. | Work with King County, Puget Sound Regional Council (PSRC) and other cities to support legislative action on a transportation funding package, including authority for increased local revenues for transit. | No policy change needed. Mayor and City Council have supported this action in the past. | Staff resources | None | None
TLU 3 | Begin construction of 23rd Avenue priority bus corridor (multimodal corridor). | Kevin/Susan | SDOT | No | Community outreach, Complete Streets analysis, traffic modeling and 30% design will be completed. | 1. Completion of remaining engineering and design. 2. Initiation of Phase I (John to Jackson) construction. | Complete Streets ordinance has shaped this multi-modal design. The Transit Master Plan, Bicycle Master Plan, and Pedestrian Master Plan have all informed the design, and the project accommodates all modes as a result of this policy guidance. | $49.550 million from various sources is identified in the proposed 2015 budget. | The total project cost is estimated to be $64.850 million (Roanoke-John-Rainier). The project is being phased through 2018. The full project scope for Phases 2 & 3 requires over $15 million in additional funding. | Public engagement continues to be a regular element of this project, with current efforts focused around preparing the community for construction. | On Track. SDOT is developing a levy proposal for MO review. Once approved by the Mayor, SDOT will work with the BTG Oversight Committee in late winter/early spring 2015 to seek input on the proposal from the public and interested stakeholders. MO will review the input and finalize the proposal and then transmit to Council for their review in time for the November 2015 general election.
TLU 4 | Complete the preliminary engineering and environmental analysis for the Center City Transit Connector. | Tony | SDOT | No | 1. Develop Draft Locally Preferred Alternative (LPA). 2. Send letter to Federal Transit Administration announcing City's intent to develop this project and eventually submit it for capital funds grant. | 1. Submit Final Draft LPA for City Council adoption. 2. Begin conceptual design 3. Complete consultant procurement for environmental analysis and preliminary engineering. | Mayor and City Council concurence required at key milestones, including locally preferred alternative (LPA) designation. | $2.5 million which includes $1.5 million in the endorsed CIP and an additional $1.0 million in the 2014 proposed budget. | $4 million in funding planned for 2015. | Scoping meeting, open houses, community meetings, on-line presence and tools. | On Track.
TLU 5 | Develop a Freight Master Plan that includes goals to make freight movement more efficient and reduce its impact on greenhouse gas emissions. | Kevin | SDOT | DPD | 1. Develop a draft scope of work and complete consultant procurement 2. Develop a project team structure 3. Develop a public engagement strategy | Most of the substantive work on the plan will occur in 2014. This will include regular briefings with a project advisory committee and other stateholder groups, developing technical analyses, and preparing a draft Freight Master Plan for public review. | There is strong policy direction in the Comprehensive Plan to protect industrial lands. The Freight Master Plan will contain goals and objectives relating to the movement of freight, and will ultimately be adopted by City Council. | $250,000 for the Freight Master Plan. There is also $280,000 budgeted for an Industrial Areas Freight Access Study, which is being done in partnership with the Port of Seattle. | None | A public engagement strategy will be developed. This will include a project advisory committee, public meetings, briefings with City boards and commissions, and on-line presence and tools. | On Track.
TLU 6 | Build bicycle lanes that are physically separated from traffic in the Center City. | Kristen | SDOT |  | 1. Begin design on two miles of the future downtown cycle track network (specific streets TBD). 2. Submit grant application for 7th Avenue cycle track. 3. Have already installed short segment of cycle track on Cherry Street. | Design will continue; some construction may begin in 2014. | The Bicycle Master Plan, currently being updated, will provide policy direction. | Funding for 30% design of the two miles is included in the Bicycle Master Plan Capital Improvement Project project. Funding for additional work is TBD. | TBD | Cycle track design will include extensive public outreach with a variety of stakeholders.
TLU 7 | Expand on-street bicycle racks and facilitate provision of off-street bicycle parking and bike sharing. | Kristen/Ann | SDOT | DPD | 1. Install 400 bicycle parking spaces in the public right of way, including eight on-street bicycle corrals. 2. Off-street bicycle parking is installed with private development as required by the SMC. 3. Legislation to support bike share program operation in SDOT right-of-way (program operation will be undertaken by private entity - Puget Sound Bike Share and Alta Bicycle Share). | 1. Install a similar number of bicycle parking spaces in 2014. 2. Continued support of bike share program, which aims to launch in 2014 with a goal of 50 stations and 500 bicycles. | Bike share use and term permit legislation requires City Council support and action. | Funding for on-street bicycle parking is included in the Bicycle Master Plan Capital Improvement Plan project. | For bike share additional private funds are needed for launch. Additional funding may be needed to expand beyond initial launch size. No additional resources are needed to continue installing on-street parking at the current level. | Bike share will conduct community outreach to educate the public about bike share and station locations. On-street bicycle parking is coordinated with adjacent businesses. | On Track. More than 500 bicycle parking spaces were installed in 2014, and a similar number is planned in 2015. Pronto bike share launched in October 2014 with 50 stations and 500 bikes. The adopted 2015 budget provides funding for future expansion.
TLU 8 | Implement bicycle intersection safety improvements on heavily traveled bicycle corridors. | Kristen/Sara | SDOT | No | 1. Install interim safety improvements along and at intersection on E Marginal Way. 2. Begin design for improvements at the Spokane/Chelan/W Seattle Trail intersection. 3. Design and outreach are underway for improvements at 50th and Green Lake. | 2014 workplan is under development. | None | Some funding is available through the Bicycle Master Plan Capital Improvement Plan project. Funding for additional work is TBD. | TBD | Public engagement varies depending on the type and scale of the project. | On Track.
TLU 9 | Improve sidewalks and crossings on arterial streets to connect Urban Centers and Villages. | Kristen/St Maint | SDOT | No | Make crossing and safety improvements at 42 locations this year. | Expect to make approximately 40 crossing and safety improvements in 2014. | None | These projects are funded through the Pedestrian Master Plan Captial Improvement Plan project. | None | Public engagement varies depending on the type and scale of the project. | On Track.
TLU 10 | Improve wayfinding and bus passenger facilities by adding electronic real-time bus schedule information and off-board payment options. | Bill/Jeff | SDOT | SCL (electricity), DoIT (fiber), KC Metro | 1. Install SDOT intelligent transportation system (ITS) kiosks at 10 locations on Third Avenue. 2. Activate and install SDOT outdoor real-time information signs (RTIS) on Rainier Avenue. 3. Install 2 SDOT storefront RTIS signs on Campus Parkway in the University District. | 1. Seek locations for additional SDOT storefront RTIS sign installations. 2. Continue installing RTIS signs on Rainier Avenue. 3. Complete SDOT ITS kiosk installation on Third Avenue. | None | Storefront RTIS signs are funded through a Transit Corridor Capital Improvement Plan project. SDOT Third Avenue ITS kiosks are funded by SDOT, King County Metro, and FTA. Rainier RTIS outdoor signs are funded through State Regional Mobility Grant and local SDOT funds. | TBD | Public engagement varies depending on the type and scale of the project. | On Track. Largely complete and on track for full completion in 2015.
TLU 11 | Implement Safe Routes projects to improve pedestrian connections to schools, transit and neighborhood business districts. | Kristen/Brian D | SDOT | No | 1. Improve walking routes at eight schools this year and begin design on additional projects for 2014. 2. Begin School Road Safety Plan in late 2013, which will guide future investments. 3. Work with OED and DON to implement the Only in Seattle program, which funds improvements in areas with paid on-street parking. | School zone speed camera revenue will fund a significant increase in the number of school safety projects. | None | Funding for school projects is included in the Pedestrian Master Plan - School Safety project. | None | Public engagement varies depending on the type and scale of the project. | On Track.
TLU 12 | Participate in multi-agency efforts working to support bike sharing, vehicle sharing and ride sharing. | Ann/Cristina | SDOT | DPD, Parks, and DON | For bike share the City has a representative on the non-profit board (Puget Sound Bike Share) and is providing support towards a planned 2014 program launch. The City routinely collaborates with King County Metro and WSDOT to identify travel options, including implementing ride share strategies. | Continue 2013 activities at the same level. | See other comments on bike share above. Council regulatory changes to support the growing demand for ride share services while meeting goals for safety, reliability, and affordability for passengers as well as fair leases for drivers could affect vehicle sharing programs. Council will be considering these issues in the fall. | Staff resources. | None | Existing outreach tools such as social media will be used to support program launch. | On Track. Legislation was adopted in 2014 addressing TNC/taxi/for hire regulations, legislation is proposed for 2015 to expand number of free floating car share operators and vehicles. There are also on-going efforts to promote use of and access to these shared mobility services by Seattle workers and residents.
TLU 13 | Work with Transportation Management Associations, property managers, employers, homeowners' associations and community groups to develop and market transit passes, car sharing and other programs that support travel options. (Cristina, MoPro) | Cristina | SDOT |  | Begin developing a Multi-Family Travel Options marketing program to provide these services. Continue to support the Commute Seattle partnership in Downtown. | Pilot Multi-Family Travel Options with residential property owners. | More resources may be needed to deliver this program on a larger scale. | State Commute Trip Reduction (CTR) funds will be used to pilot this in Center City locations. Less than $100K used for program development. | TBD - More resources will be needed to deliver this program beyond pilot sites. | Outreach will be via Commute Trip Reduction Program networks and directly to property managers. | Completed. Multifamily Development Pilot program (NAV Seattle) was conducted in several residental buidlings in 2014. The program will continue to reach additional properties and buildings in 2015. Other CTR programming continues as well as partnerships with Commute Seattle, the Center City Transportation Management Association.
TLU 14 | Support private adoption of electric vehicles by making it easier to get permits and by planning for access to charging stations and impacts on energy demand. |  | OSE | DPD, SDOT, FAS, SCL, SPL, Police, Fire, Law, Labor Relations | 1. Complete study on increasing access to charging stations. 2. Develop recommendations based on results of the City Publicly Available Charging Station in City Garages pilot program. 3.Track locations of charging stations on private property to evaluate and respond to impacts to electical distribution infrastructure. | 1. Implement study recommendations to increase access to charging, including developing public/private partnerships. 2.Track City EV fleet environmental impacts. | 1. Decisions will be needed concerning continuing to provide publicly available charging station services in City garages. 2. Decision to provide access to charging infrastructure for employees' personal electric vehicles. | Staff resources and consultant support. | TBD | TBD - based on study results. | On Track.
TLU 15 | Develop a Green Fleets Plan for City of Seattle fleet that encourages market adoption of next generation vehicles and fuels. |  | FAS | Parks, SPU, SCL, SDOT, Fire, Police, OSE | Prepare a Green Fleets Action Plan framework to achieve the million gallon fuel challenge and contribute to meeting citywide climate action goals. | Work with departments to prepare a Fuel Reduction Opportunities Assessment and Implementation Plan. | Policy needs may arise as the plan develops. | Staff resources | None | Internal outreach and media release. | Completed. A fuel reduction IDT is being formed to support implementation.
TLU 16 | Expand the City's municipal electric vehicle fleet. |  | FAS | Parks, SPU, SCL, SDOT, Fire, Police, OSE | Purchase 36 new electric vehicles including sedans and SPD parking enforcement vehicles. | Convene an interdepartmental team to evaluate City building infrastructure needs to support expanded municipal electric fleet. | None | Capital replacement funds. | TBD | TBD | On Track. $900K in CIP funds were allocated in 2015 for infrastructure to electrify the Parking Enforcement fleet (78 vehicles). More funds will be required to build out additional infrastructure as fleet electrification continues.
TLU 17 | Develop equitable development policies to support growth and development near existing and planned high capacity transit without displacement as part of the 2015 Comprehensive Plan major review. |  | DPD | OH | Major review of the Comprehensive Plan - Housing Element, and a review of affordable housing incentives. | Major review of the Comprehensive Plan- Housing Element and review of the Incentive Zoning program. | New or revised policy in the Comprehensive Plan; changes to the Incentive Zoning program. | Staff resources and consultant resources to develop a public engagement plan and develop the Comprehensive Plan EIS. | TBD | Comprehensive Plan major review will include public engagement - the engagement plan is under development. An Affordable Housing Incentive Advisory Committee is providing input. | On Track. DPD and OH are providing staff support to the Mayor's Housing Affordability and Livability Agenda committee that will be exploring ways to provide housing affordable to all income groups in the city.
TLU 18 | Continue to implement local area plans and urban design frameworks in Capital Hill, Broadview/Bitter Lake/Haller Lake, Rainer Beach, Othello, Mount Baker, Beacon Hill, Northgate, and the University District. |  | DPD | SDOT, OH | Different project are at different stages including developing and implementing scopes of work, conducting public engagement, developing existing conditions analyses and preliminary recommendations. | Conducting public engagement and implementing comprehensive plan and zoning changes as needed. | Adopting legislation to change zoning and/or comprehensive plan policy as needed. | Staff resources and consultant resources for some projects. | None identified at this time. | Public engagement generally includes project website, community workshops, community resource fairs, advisory committee, community action teams, surveys, polls, and other online engagement through website and social media. | On Track Work is ongoing in the listed neighborhoods as well as Ballard, Lake City, Uptown. The U District zoning changes will be advanced in early 2016.
TLU 19 | Implement the Challenge Grant strategies in the Rainier Valley to prevent displacement and retain affordable housing near transit. |  | OH | DPD, DON, OED, OCR | Award funds to a developer for the acquisition of one parcel for an affordable housing and mixed-use project. Launch a commercial technical assistance program for locally owned businesses. Formalize a coalition of immigrant and refugee community based organizations to plan for a shared multi-cultural center. | Award funds to a second developer for the acquisition of a Sound Transit parcel at the Othello station for an affordable housing and mixed-use project. Continue the commercial technical assistance program. Present a Business Retention and Attraction Plan for the Othello commercial district adn launch an implementation strategy. Conduct a feasibility study for a shared multi-cultural center. | Commitment to provide permanent sources of financing for the long-term development and management of affordable housing near transit in SE Seattle. | $7 million for land acquisition. $850,000 for commercial stabilization strategy. $400,000 for shared multi-cultural center planning. | Permanent sources of financing for long-term development and management of affordable housing. Commercial pre-development and tenant improvement funds for the business retention and attraction strategy. Pre-development funds for the shared multi-cultural center. | Semi-annual large community gatherings to report on progress made in planning a shared multi-cultural center. A large community meeting to present a Business Retention and Attraction Plan and launch the implementation strategy. | On Track. The Equitable TOD Loan Program made three awards for land acquisition of vacant properties near light rail stations in SE Seattle. In addition to providing up to 290 units of affordable housing (50% of which will be 2 and 3 bedroom units), these projects will deliver a host of other community benefits, such as 40,000 sq. ft. of commercial space, which uses may include but are not limited to: childcare, public community gathering space, office space, and a community center.
TLU 20 | Develop a tool to foster consistent consideration of greenhouse gas emissions impacts and opportunities to reduce them when updating and implementing transportation and land use policies. |  | OSE | DPD, SDOT | Collaborate with departments to identify opportunities and develop a test version of the tool or guide. | Update the resource based on departmental feedback and pilot testing and launch the resource. | None | Staff resources | None | Internal outreach through existing staff and interdepartmental team meeting forums. | Not Initiated. A broadly applicable tool was determined not to be effective. Instead OSE climate staff continue to participate on interdepartmental teams to support context-specific climate input and build transportation and land use planning staff capacity.
TLU 21 | Develop a placemaking strategy for using our public spaces to make streets and neighborhoods more vibrant and to promote economic activity. Implement a project reallocating a portion of the public right-of-way to a public/pedestrian space, such as a plaza or parklet. | Jennifer | SDOT | Nearly all departments have some role | 1. SDOT presented the Public Space Management Program implementation strategy and 2013 work plan to Council in June. The program includes 23 initiatives that are prioritized based on recommendations from a 34-member Public Space Management Task Force. 2. 2013 deliverables include research on alley activation and design standards; development of a request for proposals for a Coordinated Street Furniture Program; launch of the Pilot Parklet Program; identification of pilot sites for a "pavement-to-parks" program; and new communications materials. | The program's implementation strategy includes 5-year implementation actions for each program area. The 2014 work plan will be based on these 5-year actions. SDOT will provide Council with a detailed 2014 work plan in late 2013. 2014 tasks could include: 1. Launch of a formal Parklet Program. 2. The Coordinated Street Furniture Program will select a vendor and begin preparing legislation for changes to the sign code. 3. Install a public loo in Pioneer Square. 4. Adopt a Director's Rule to address placement and maintenance standards for news boxes. 6. Propose a new permitting structure for business and neighborhood amenities. | No policy changes are needed to continue implementation. However, many of the program areas require legislation to achieve full implementation. For example, the Coordinated Street Furniture Program will require the adoption of legislation to change the sign code to allow off-premise advertising. | The 2014 proposed budget includes $782,000 and 3 new FTEs. | To fully implement the program, grant funding for community-generated projects should also be considered. $680,000 is currently a planning assumption for 2015 | The program's implementation strategy was developed by a Task Force of 34 people, including City staff and members of the public. Staff have briefed community groups on request and will develop a more comprehensive outreach plan for the program later in 2013. Significant outreach has occurred for specific program areas, such as the Pilot Parklet Program. | On Track. The Pilot Parklet Program (launched in 2013) will transition to a permanent program in 2015; 5 parklets are already built in the city and 10 more are in the pipeline. We are currently piloting a Play Streets Program (through May 2015) that allows residents to turn a street into a place for kids of all ages to play on a recurring basis. A Pilot Pavement to Parks/Plazas Program is planned for initiation in 2015-2016. The Public Space Management Program has expanded to 40+ program areas in 2014, and we are focused on making great places in the right-of-way through our implementation.
TLU 22 | Implement strategies to provide residents' daily needs within a convenient walk and create nodes well served by transit and non-motorized transportation options. |  | DPD | SDOT, OH | The major review of the Comprehensive Plan including the Land Use and Urban Village elements and local area plans include policies and actions to support complete, connected neighborhoods. | The major review of the Comprehensive Plan including the Land Use and Urban Village elements and local area plans include policies and actions to support complete, connected neighborhoods. | Comprehensive Plan updated distribution of growth; mitigation of impacts for the preferred alternative, zoning changes associated with local area plans, and public realm concepts. | Staff resources and consultant resources for some projects. | None identified at this time. | Public engagement generally includes project website, community workshops, community resource fairs, advisory committee, community action teams, surveys, polls, and other online engagement through website and social media. | On Track. The Comprehensive Plan update will be completed in 2015. The basis of the existing Plan is the urban village strategy, which focuses new housing and employment growth in urban centers and urban villages and directs public services, inlcuding transit, to those areas. The update of the Plan will look for ways to strengthen this strategy in order to further reduce reliance on auto travel to meet daily needs.
TLU 23 | Create a grant program that supports walking, biking and transit projects in business districts with paid parking. |  | OED | SDOT | The Only in Seattle Program was established and includes $500,000 in SDOT's budget to support capital improvement projects that enhance business districts. Participating neighborhood business districts that have paid on-street parking are eligible to submit proposals. | Ongoing program | None | 500000 | None | The Only in Seattle program includes an extensive marketing component. OED conducts direct outreach to promote awareness of the grant program. | On Track. The Commercial Stability Strategy has supported dozens of businesses in the Othello/Graham business district through business technical assistance workshops, individual technical assistance grants, business promotion programs, façade improvement programs, and other wrap-around services. The strategy also resulted in the formation of a coalition of businesses, community organizations, and land owners to implement a vision of economic development for the area. This coalition, called On Board Othello, launched a branding and promotion strategy as well as a business retention and attraction strategy in 2014.
TLU 24 | Work with neighborhood districts to develop on-street parking management and other access strategies. | Cristina/ Jonathan | SDOT | DPD, OED, DON | Begin work in Chinatown-ID and Pioneer Square, continue work in Ballard. Focus on changes to on-street parking regulation and access themes. | 1. Assuming 2013 funding levels, work will be complete in Chinatown-ID, Pioneer Square, and Ballard. Work will be scoped in two additional neighborhoods. 2. Explore whether/how program role can be expanded to address multimodal neighborhood business district access. | None | Staff resources and a $60,000 annual budget. | None | Community meetings, surveys, open houses, and online presence. | On Track.
TLU 25 | Expand the e-Park program in the Center City to reduce the need to drive around while finding parking. | Meghan/ Michael | SDOT | City Light, DON | The e-Park Phase 2 expansion is underway now, with five additional garages joining the program in 2013 - primarily in the Pioneer Square and Central Waterfront neighborhoods. | In 2014, e-Park will complete the installation of the right-of-way dynamic and wayfinding signs that support the 2013 Phase 2 expansion. The addition of up to 5 additional garages in the Center City may also be included in 2014, as well as preliminary planning for a Phase III expansion to SODO and Seattle Center. | None | The Phase 2 expansion is funded. SR 99 mitigation funds are used to cover garage costs to increase the number of Pioneer Square and Central Waterfront garages in the program. Phase 3 is not funded. | Expansion of e-Park to the financial district and Chinatown/ID requires funds to off-set garage costs to enter the program and remove barriers to entry (approx. $15K per garage). Preliminary cost estimate for Phase 3 expansion which is anticipated to start in 2015 - 2016 is $4.5M. | Public education about e-Park is conducted through an annual marketing/public education campaign. | On Track. At the end of 2014, there are 13 garages in the program. Dynamic sign installation is underway and will be complete in 1Q 2015. Per a new agreement, Commute Seattle will take the lead on promoting e-Park and integrating it into the DowntownSeattleParking.com campaign promoting short-term, off-street parking availability.
TLU 26 | Update and maintain a Seattle travel demand model in order to implement the monitoring framework. | Kevin/Jude | SDOT | DPD OSE | SDOT works with the Puget Sound Regional Council (PSRC) and consultants to do travel demand modeling to support transportation planning work. PSRC is developing a business model for how to provide travel demand modeling services to member jurisdictions and their consultants. The region is shifting from a traditional 4-step model to an activity-based model that is more granular, but likely cost-prohibitive for individual jurisdictions to maintain on their own. Instead, PSRC is likely to provide the base model to jurisdictions/consultants for their use in analyzing alternative scenarios. | SDOT, DPD, and OSE staff will work with PSRC to identify modeling needs for City projects, including the update of the City's Comprehensive Plan, the Freight Master Plan, and implementation of the Climate Action Plan. | The current direction is to continue to rely on PSRC and consultants to perform modeling to support city transportation planning and other initiatives. Alternatively, the City could re-establish its travel demand model. | There are resources identified in the proposed budget for the Comprehensive Plan update that include travel demand modeling support. There are no identified resources for Climate Action Plan support. | The current direction is adequate to meet our basic needs on large-scale projects with consultant budgets. However, the City could consider re-establishing in-house travel demand model analysis capabilities or on-call consultant services in order to conduct additional analyses, such as performance monitoring for the CAP and other needs. This would require multiple FTEs (or a combination of FTEs and consultants) and resources for computer hardware, software licenses, analysis and data maintenance. | No public engagement is planned, as travel demand modeling supports work on projects with their own public engagement plans. | Not initiated. The need is being met through other avenues. SDOT and DPD have engaged consultants to perform modeling for the City's Comprehensive Plan and companion Environmental Impact Statement. City-specific modeling methodology / specifications have been identified during Plan and EIS development, which can be applied to Climate Action Plan tasks, as required.

## Building Energy
Building Energy
| Action | Lead staff | Lead Dept | Other Depts | 2013 Implementation Tasks | 2014 Implementation Tasks | Needed Policy Decisions | Existing Resources | Needed Resources | Public Engagement | Implementation Status
BE 1 | Begin implementing a plan to deploy smart meters that provide real-time energy use information to all Seattle City Light customers. |  | SCL |  | Hire project manager, establish project team, hire expert educational consultant, develop workforce development plan for impacted employees. | Adopt health and privacy policies, develop a business case and submit a Budget Issue Paper, develop and issue a Request For Proposal for implementation. | Decision to proceed with implementation. | Strategic Plan includes placeholder for funding from 2015-2018. | Strategic Plan includes placeholder for funding from 2015-2018. | Community forums, outreach to businesses and organizations, website, surveys, info sheets/FAQs, e-bulletins, DON liaisons. | On Track. The AMI Program Manager was hired and the AMI HR Plan, Budget and Project Timeline have been developed. An Advisory Team and a Steering Committee were convened. Process is underway to hire a consultant to assist in evaluating three potential AMI technologies (MESH, STAR, and LTE).
BE 2 | Make the energy benchmarking scores of the City's municipal buildings publicly available. |  | OSE | FAS, Parks, Seattle Center, SPL, SDOT, SCL, SPU | 1. Benchmark City buildings in accordance with, and beyond, the requirements of the City's Energy Benchmarking and Reporting Ordinance. 2. Produce an Energy Performance Report for municipal buildings and make it readily available to the public. | 1. Benchmark City buildings in accordance with the requirements of the City's Energy Benchmarking and Reporting Ordinance. 2. Benchmark relevant City buildings less than 20,000 sf. 3. Produce an Energy Performance Report for municipal buildings and make it readily available to the public. | As part of Mayor's Office approval of the Resource Conservation Management Plan, determine whether municipal facilities should benchmark and report buildings below the 20,000 square foot requirement | $7,500 in grant funds (2013) to develop the intial report format and content; OSE staff time to develop report; FAS, Parks, SC, SPL, SDOT, SPU staff time to benchmark buildings. | None | Press release, website. | Completed.
BE 3 | Develop a Resource Conservation Management Plan to guide efficiency investments in City facilities, including developing a strategy for routinely conducting "tune ups" of City facility energy systems (known as retro-commissioning). |  | OSE | FAS, Parks, Seattle Center, SPL, SDOT, SCL, SPU | 1. Finalize Draft Resource Conservation Plan. 2. Develop guidelines for resource efficient best practices. 3. Conduct building energy audits and implement Operations and Maintenance (O&M) targeted efficiency improvements. | 1. Establish centralized resource consumption tracking. 2. Implement O&M targeted efficiency improvements. 3. Undertake studies to identify the costs and benefits of capital based efficiency improvements. 4. Conduct additional building energy audits. | Adopt plan, provide direction to departments to track energy and water consumption data in a resource accounting system. | Grant funds have supported OSE staff time and consultant expenses in 2012 & 2013. The 2014 proposed budget includes resources to make the Citywide Resource Conservation Advisor a permanent position ($127,500 ) and resources to implement the Plan ($250,000). |  | Public release of Plan through City website. | Completed.
BE 4 | Require building energy audits for the largest and less efficient commercial and multifamily buildings to help identify cost effective and operational improvements. |  | OSE | DPD, SCL | Monitor best practices, benchmarking results, and energy code updates. | Launch working group to recommend a policy design, conduct outreach and begin defining policy. | Mayor/Council approve specific policy elements; consider incentive or assistance options. | Staff resources | TBD | Working group of impacted stakeholders, additional stakeholder outreach. | Not Initiated. Work was subsumed under the more comprehensive effort to develop a broad package of building energy efficiency policies and programs, with completion anticipated in 2016.
BE 5 | Pilot a retro-commissioning incentive program to provide financial and technical assistance to tune up energy systems in existing commercial buildings. |  | SCL | None | Continue implementation of twelve projects currently underway. | Complete implementation and assess results of pilot efforts. | Whether or not to implement retro-commissioning as standard offer as part of portfolio of programs to meet energy savings targets. | Included in overall conservation incentive budget. | None | Engage current participants to assess pilot; outreach to customers, if offered as standard program. | Completed a pilot retro-commissioning incentive program and plan to develop/roll out a full-scale program in 2015.
BE 6 | Maintain the City's commitment to low-income weatherization services by continuing to seek resources for the HomeWise program. |  | OH | SCL, OSE | Weatherize the homes of low-income homeowners and rentals occupied by low-income tenants to help make these buildings more energy efficient helping low-income Seattle residents save energy and money. | Weatherize the homes of low-income homeowners and rentals occupied by a low-income tenants to help make these buildings more energy efficient helping low-income Seattle residents save energy and money. | None | Funding from Seattle City Light, Puget Sound Energy (PSE), Washington State Department of Commerce | With American Recovery & Reinvestment Act (ARRA) dollars HomeWise was able to increase its capacity, especially to serve multi-family buildings. With the end of ARRA funding, other sources of funding and/or financing are needed, especially to continue serving multi-family buildings at the same or greater level. | HomeWise will continue its normal methods of marketing and promoting our programs. | Completed & ongoing
BE 7 | Pass state legislation to authorize a property tax exemption for rental housing owners who undertake significant upgrades to increase energy efficiency. |  | OSE | OIR | None | Develop draft legislation; build support and legislative strategy. Advocate for adoption by state legislature. | Confirmation of Mayor/Council support for an exemption program. | Staff resources | None | Will be developed for City program in 2014 if state legislation passes. | On Track.
BE 8 | Partner with property owners and managers to identify the most compelling financing tools for energy efficiency upgrades in commercial buildings and outline a plan to help bring them to market. |  | OSE | SCL | None | Coordinate with outside organizations (e.g. BOMA and 2030 District) to identify needs and interest; research best practices | None to implement this action of identifying the tools. Next steps, based on findings, may require policy decisions. | Staff resources | None | Engage commercial building stakeholders through an informal stakeholder working group. | Not Initiated. Work was subsumed under the more comprehensive effort to develop a broad package of building energy efficiency policies and programs, with completion anticipated in 2016.
BE 9 | Continue improving permitting processes to promote the most sustainable buildings, such as the Living Building and Deep Green Pilot Program. |  | DPD | OSE, SPU, SDOT | 1. Convene Living Building and Deep Green Technical Advisory Group. 2. Deliver legislation revising the Living Building Pilot Program. 3. Update Priority Green eligibility thresholds to adapt to changes in construction codes and green building certification programs. | Develop legislation implementing a new Seattle Deep Green pilot program. | Mayor/Council decision on what level of flexibility and/or incentives are needed to promote more sustainable buildings and how to ensure compliance with performance requirements. | Staff resources | None at this time. Future resources may be identified as part of the update to the program. | Technical Advisory group will work with staff throughout process Public meetings for stakeholder input will be held in 2014. Stakeholder outreach on new Priority Green eligibility thresholds. | On Track.
BE 10 | Partner with Seattle Public Schools to identify opportunities to build Living Building Challenge or Deep Green schools. |  | OSE | None | Meet with Seattle Public Schools (SPS) Facilities staff to share best practices for City buildings. Provide SPS access to City-developed green building strategies toolkit, Capital Green and associated training curriculum. | Periodic coordination with SPS to share approaches and resources. Engage additional stakeholders to evaluate options for moving toward goal. | None | Staff resources | None | None | Completed.
BE 11 | Continue increasing energy efficiency standards in the Seattle Energy Code over time. |  | DPD | None | Implement 2012 Seattle Energy Code Chart incremental energy use targets for each 3-year cycle through 2030. | Education & user support for 2012 Energy Code. City approval of future energy use targets. | Mayor/Council reaffirm commitment to targeted energy use reductions. | Staff resources | None | Public meetings for stakeholder input | On Track.
BE 12 | Develop an alternative energy master plan that focuses on low-carbon energy solutions, such as district energy and siting of solar and geothermal energy in the public right-of-way. |  | OSE | SCL, DPD, SPU | None | 1. Launch master planning effort 2. Establish working group 3. Set goals and priorities 4. Establish plan framework | Mayor's Office policy decisions about scope and direction of master plan. | Staff resources | None | Public input into master plan through multiple media and venues; specific engagement strategy to be developed with project scoping. | Not Initiated. Due to insufficient resources, OSE's focus was on the following priority actions: a. Transition Community Power Works Home program to an established program; b. Expand district energy systems on First Hill and into the South Lake Union & Denny Triangle neighborhoods.
BE 13 | Maintain Seattle City Light's commitment to conservation and renewables, as well as to providing carbon neutral electricity. |  | SCL | None | Achieve 14.0 aMW energy conservation, support customer renewables, and maintain greenhouse gas neutrality. | Achieve 14.0 aMW energy conservation, support customer renewables, and maintain greenhouse gas neutrality. | Confirmation of energy savings target through SCL Strategic Plan update. | $45.5 million in Capital Regional District for conservation and customer renewables; $1.2 million for carbon offsets. | None | Outreach through strategic planning process; outreach and marketing to customers for participation in conservation and renewable programs. | Completed. Ongoing - Seattle City Light remains committed to achieving 14 aMW of conservation-related energy savings, to supporting customer renewables and to maintaining its greenhouse gas neutrality.
BE 14 | Continue Seattle City Light support for solar energy through net metering, which reduces the quantity of electricity billed to the customer by the amount of solar energy produced. |  | SCL | None | Continue to implement net metering policy and comply with State requirement. | Continue to implement net metering policy and comply with State requirement. | None | Renewable production incentives funded by State. | None | Promotion of solar through Solarize campaigns, web, newsletters, outreach, and demonstration projects. | Completed. Ongoing - participation in SCL's solar energy programs continues to grow.

## Waste
Waste |  | SPU BAM
| Action | Lead staff | Lead Dept | Other Depts | 2013 Implementation Tasks | 2014 Implementation Tasks | Needed Policy Decisions | Existing Resources | Needed Resources | Public Engagement | Implementation Status
W1 | Support and collaborate on ongoing state, regional, and national programs and policies to encourage product stewardship of electronics and other materials. | Dick | SPU | SCL | SPU will continue to work with the Northwest Product Stewardship Council (NWPSC) and Local Hazardous Waste Management Program on legislation to create extended producer responsibility (EPR) laws. | 2013 tasks will continue. | The Solid Waste Management Plan contains policy support for these actions. | Staff & program resources | None | NWPSC already does extensive outreach to solid waste agencies and their constituencies that focus on specific legislation and EPR in general. This will continue. | Completed. Ongoing - SPU supported hiring full timeNWPSC coordinator for 2014-15. Major responisbility is outreach to local governments and solid waste industry.
W2 | Pursue local product stewardship programs, such as take-back requirements for select products that are not included in state or regional programs and reduce product packaging. | Dick | SPU | None | SPU is awaiting possible state action before moving ahead with local retail take-back requirements. | Level of state action will be re-evaluated before considering local take back of batteries, medical sharps, and other items. | The Solid Waste Management Plan and the Zero Waste Resolution provide support for these actions. | Can be accomplished within existing SPU Solid Waste Division and Resource Conservation budgets. | None until implementation then 1/2 FTE for outreach. | None until local action proposed, then extensive stakeholder outreach with retail businesses. | On Track.
W3 | Launch programs to support edible food donation, help commercial kitchens find efficiencies and reduce waste, and help households and businesses reduce food waste through better planning, purchasing, storage and preparation. | Dick | SPU | None | Pilot study by 100+ households examining level of food waste and how it can be reduced. | Promote household food waste reduction strategies through SPU communication tools. | The Solid Waste Management Plan and the Zero Waste Resolution contain support for these actions. | State grant funding (Coordinated Prevention Grant) is anticipated to fund program. | None | Media, mostly direct mail. | Completed. Household food waste reduction strategies have been planned, with implementation in 2015.
W4 | Continue to support opt-out programs for junk mail. | Dick | SPU | None | Continue the Catalog Choice contract service. | Continue the Catalog Choice contract service. | None. Program is ongoing. | 25000 | None | Direct mail outreach to residents to maintain awareness of program. | Completed. Ongoing -SPU supported hiring full time NWPSC coordinator for 2014-15. A major responisbility of the coordinator is outreach to local governments and the solid waste industry.
W5 | Implement new recycling and composting programs for residential and business waste, including programs that target waste hauled by residents to transfer stations. | Hans | SPU | None | Research and test station sorting of Construction & Demolition (C&D) recycling and other large items. Also see self-haul options in other actions. | Implement station sorting. (Plus new bans and self-haul services described in other items.) | None | Staff resources | TBD | TBD | On Track. A C&D sorting pilot was completed in 2014. Results are being evaluated for potential implementation in 2015.
W6 | Increase enforcement of residential and business recycling and composting requirements. | Hans | SPU | None | More aggressive garbage container monitoring with existing staff. | Continued container monitoring, plus station floor monitoring of large roll-off customers. | None (potential staffing decisions). | Staff resources | TBD | None | On Track. Field container monitoring was expanded 2014. Station container monitoring piloted 2014, to expand 2015.
W7 | Ban the following materials from residential and business garbage to increase recycling: asphalt paving, concrete, bricks, asphalt shingles, plastic film , clean wood, residential food, and compostable paper. | Gabriella & Hans | SPU | None | None | 1. Consider legislation to ban food waste from garbage for households (2014), apartments (2015) and businesses (2016). 2. Consider legislation to ban beverage containers, wood and film from buinsess garbage. | New legislation | Staff resources | TBD: Outreach could require new or reallocated resources. | TBD | On Track. In 2015, food waste will be banned in all sectors. Beverage containers and other recyclables were banned from business garbage starting in 2014.
W8 | Phase-in bans on the following construction and demolition waste from job sites and private transfer stations: recyclable metal, cardboard, plastic film, carpet, clean gypsum, clean wood, and asphalt shingles. | Gabriella | SPU | DPD | 1. Outreach Plan Development 2. Newsletter articles, presentations to construction trade associations, property management associations, recyclers, haulers and processors 3. SPU Rulemaking for implementing the Construction & Demolition (C&D) recycling facility certification program and waste diversion submittal process. 4. SPU IT to develop Waste Diversion Report Form and database. 5. Create Client Assistance Memos and other educational resources for new programs. | 1. Increased outreach to wider range of audiences such as public and private transfer station customers. 2. Initiate monitoring program of Waste Diversion Report submittals. 3. Certify recyclers and mixed waste receiving and processing facilities through monitoring and sampling program. 4. Contract with recyclers for accepting commingled C&D materials tipped at City transfer stations for recovering banned materials. | Issues may develop with 1) the certification process as far as certain facilities being listed or not listed and 2) how the City chooses to enforce the disposal bans at its own transfer stations. Initial decisions and instructions on transfer station disposal bans will be based on results of a current pilot. | $40,000 - $60,000 supporting DPD's educational efforts and waste diversion report, maintenance of Waste Diversion Report electronic web form, sampling for facility certification, and field outreach to construction contractors. The 2014 proposed budget includes resources for more comprehensive facility monitoring, field staff to visit construction sites and transfer stations with educational materials , as well as development of new public outreach mechanisms. | TBD | Multiyear public engagement process with focus initially on major stakeholder interest groups such as the AGC, Master Builders and also minority contractor organizations. Will expand in 2014 to include more general audiences such as home remodelers and junk haulers. | Completed.
W9 | Expand investment in existing residential and business programs for reuse and organics management to reach more residents and businesses. | Dick | SPU | None | Mulch mowing promotion through a Coordinated Prevention Grant. Reuse option promoted via customer outreach tools. | Program funding such as mulch mowing will be undetaken when additional funding such as grants are available. Reuse will continue to be promoted via customer outreach tools. | 2014 spending plan review (SPU Solid Waste Division and Resource Conservation Division review program emphasis areas, which could lead to budget adjustments.) | TBD | TBD | TBD | Completed.
W10 | Continue to support and expand material exchanges and reuse programs, and promote building with salvaged and reclaimed materials. | Dick | SPU | None | This work has been scaled back due to personnel cuts in Corporate Strategies. | Modest promotion will continue in connection with Construction & Development (C&D) disposal bans and processor certification program. | Supported by Solid Waste Management Plan and Zero Waste Resolution. | Staff resources | Expansion would require evaluation of budget. | Outreach is connected with C&D material bans and processor certification process. | Completed.
W11 | Make reuse and recycling drop-off more convenient at transfer facilities. | Jeff | SPU | NA | Design of the North Transfer Station (NTS), including space programmed for reuseable drop off. | Construction of NTS and initiation of South Transfer Station (STS) Phase 2 design work that will include reuseable drop off and retail sale space. | These decisions were covered in the Solid Waste Facility Master plan as well as the Solid Waste Management Plan. | Both Capital projects are funded and we will be evaluating Operations & Maintenance requirements next year. | None | There has been extensive community outreach is ongoing for NTS. STS phase 2 will also include community outreach. | Completed.
W12 | Enhance outreach and education about recycling and composting to both residents and businesses. | Hans | SPU | None | Redirecting funds in second half of 2013 to boost food recycling through a media campaign that encourages more food recycling by residents and businesses. | Continued food recycle outreach, recruiting and assistance, | 2014 spending plan review. | 2013 - $425k non-labor; 2014 - $425k non-labor | TBD | Media outreach, direct mail, promotion partnerships, tenant account assistance at large accounts, and under-served outreach. | Completed & ongoing.
W13 | Pilot and consider changing garbage collection from single-family homes to every-other-week . | Hans | SPU | None | 1. Submitted final report on pilot to Council. 2. Soliciting input from advisory groups. | Make final decision on any desired service changes for 2015. | City decision 1Q14 for potential every-other-week (EOW) garbage in 2Q15 or later. | 2013 - $65k non-labor to complete pilot; 2014 - none | None | 1. Advisory group input in 4Q13. 2. Transition outreach in 4Q14 if EOW garbage selected | Completed. The pilot was completed. Based on the results from the pilot, this not being implemented.
W14 | Focus grants on schools to establish system-wide collection for food and yard waste. | Dick | SPU | None | Budget for these grants has been eliminated. | None, though progress monitoring by staff will continue. | Council would need to reaffirm importance and fund. | None | TBD | None | Not initiated. Due to lack of funding.

## Preparedness
Preparing for Climate Change
| Action | Lead staff | Lead Dept | Other Depts | 2013 Implementation Tasks | 2014 Implementation Tasks | Needed Policy Decisions | Existing Resources | Needed Resources | Public Engagement | Implementation Status
A1 | Apply the planning methodology detailed in the City of Seattle Sea Level Rise Planning Guidance for Capital Projects to projects projected to be impacted by sea level rise. |  | OSE | SPU, SDOT, Parks, SCL, FAS | Update the document based on latest projections. Pilot test the the approach on two major capital projects. | Make any needed revisions to the approach. Provide training on applyng the guidance to staff in capital departments. | Executive direction to employ the evaluation methodology to large capital projects in areas at risk of more frequent flooding due to sea level rise. | Staff resources | Departments may determine that additional investment is needed for individual projects to enhance resilience to sea level rise. | Internal outreach to capital departments. | On Track. This effort is being integrated into the more comprehensive Climate Preparedness Strategy. The guidance will be updated and piloted in 2015.
A2 | Use thermal imaging to identify areas that are most likely to be impacted by heat events. This will inform development of urban forest and tree planting priorities and programs. |  | SPU | SDOT, OSE, Parks | Identify thermal imagery data sources that can be used to create a City GIS layer. | Create a layer in the City's GIS system that can be overlaid with the tree and vegetation canopy layer. Use results to target tree planting in problem locations through the Trees for Neighborhoods program and SDOT's street tree planting. This information would be used in the possible development and management of forest eco-hoods. | None: This work fits within the policy direction established in the Urban Forest Stewardship Plan. | Staff resources | None expected | Information on heat islands and opportunities to use vegetation to help mitigate heat impacts will be incorporated into the reLeaf website and outreach materials. | Not initiated. Need is being met through other actions. Infrared data collected in summer, which is needed to capture the presence of heat islands, is not available and is cost prohibitive to collect. However, staff are evaluating potential surrogate indicators (e.g. presence of impervious surfaces) to provide the information needed to inform tree planting prioritites relative to heat islands.
A3 | Maintain efforts to restore all 2500 acres of forested parkland by 2025 through the Green Seattle Partnership. |  | OSE | Parks, SPU | Maintain 865 acres in restoration, plant 30,000 trees and shrubs, bring 60 new acres into restoration, maintain and educate 130 volunteer Forest Stewards, support, promote, and track outcomes for least 800 volunteer events. | Maintain 910 acres in restoration, plant 28,000 trees and shrubs, bring 45 new acres into restoration, maintain and educate 135 volunteer Forest Stewards, support, promote, and track outcomes for least 700 volunteer events. | Ongoing financial support is primarily Capital, policy decisions are required to replace or supplement this funding with permanent Operations &Maintenance or other sources. | Currently $2.5 million annually in Captial Improvement Program and Levy funds until 2015. $100K from SPU Opearations & Maintenance funds. | The program needs an additional $1.3 million annually to start closing the current gap in funding and stay on track with the original 20 Year Plan benchmarks. Without any additional funding the gap will grow to and estimated $4 million by 2014. | Public engagement is significant with about 800 volunteer events and 75,000 volunteer hours a year. Engagement includes 3 major public events that each draw 500-1000 people. Community outreach includes ongoing youth employment programs with non-profits: Goodwill, Earthcorps, Nature Consortium, Washington Conservation Corps, and efforts to engage more community groups in focus neighorhoods (Rainer, White Center, Bitterlake Columbia City, Rainer Beach/Valley Beacon Hill South Park Delridge Highland Park Holly Park) to their local forested park. | Completed. Efforts to meet the 2025 goal are ongoing.
A4 | Implement the Urban Forest Stewardship Plan. | OSE | OSE | SPU, Parks, DPD, FAS, SCL, SDOT, S Ctr, | Finalize Plan update. Adopted by Council. | An implementation strategy for the Urban Forest Stewardship Plan's short-term actions identified by Council is underway and anticipated to be completed by the end of 2013. The strategy will include tasks, schedule, policy decisions, and needed resources. |  |  |  |  | On track.
A5 | Implement projects in several ubran creeks that connect floodplains, increase stormwater storage capcity, and imporove culverts to minimize flooding and improve habitat. |  | SPU | Parks, SDOT | Knickerbocker Floodplain Improvement Project (construction 2013-2014); NE 93rd Culvert (construction 2013-2014); Taylor Creek Culvert (design 2013-2014). | Knickerbocker Floodplain Improvement Project (construction 2013-2014); NE 93rd Culvert (construction 2013-2014); Taylor Creek Culvert (design 2013-2014). | These projects are in the SPU Capital Improvement Program and are critical to reducing flooding impacts to residents and eliminating fish passage. | Approximately $900k in 2013 and $7.2 million in 2014. | None at this time. | In all cases efforts are made to engage effected area residents. Public engagement strategies are tailored depending on scope and impacts of the project. | On Track. The Knickerbocker project is in final construction. NE 93rd Culvert project construction has been completed (though project is smaller than originally conceived). Taylor Creek design is nearing completion.
A6 | Evaluate climate change impacts on electricity resources and future energy demands using applied research and modeling beyond the 20-year planning horizon currently used in the Integrated Resource Plan. |  | SCL | None | The 2012 Integrated Resource Plan assess a need to understand changes in glacier contribution to the Skagit basin. Resource planning beyond the 20-year horizon will be informed by a collaborative effort (see action below) to inventory and model historical and future glacier contributions to streamflow in the Skagit river and tributaries. | The 2014 Integrated Resource Plan (IRP) will be updated to include new research from the glacier assessment and the latest climate change projections. An updated hydrology model with glaciers incorporated will be in development during 2014. | It is not current policy to require resource planning beyond the 20-year planning horizon. Longer-term planning will need to be supported by policies within the utility and the city. | No additional resources are budgeted beyond the current climate change research budget. | A City Light climate preparedness strategy is under development which will identify additional actions which may require funding. | In addition to the public process for the IRP, SCL will provide information on climate change impacts and adaptation actions to customers as needed. | On Track.
A7 | Collaborate with external partners to research the impacts of climate change on hydroelectric projects, including impacts on generating facilities and salmon survival. |  | SCL | SCL | SCL established an Memorandum Of Agreement with the National Park Service (NPS) to assess historical and future contribution of glaciers to the Skagit River Project. Research will show changes in summer water resources for hydropower generation and instream flows for fish. Funds will be allocated to incorporate results of the glacier study into a more comprehensive model of future streamflow for the Skagit basin. SCL, in collaboration with SPU, acquired the most recent climate projections, which will be used in adaptation planning. SCL is collaborating with the Clean Energy Group (CEG) that consists of electric utilities that are sharing information on climate change adaptation strategies. | SCL will collaborate with NPS and university scientists to continue the modeling of streamflow in the Skagit basin. Funds from the climate change adaptation initiative will be allocated to research that increases understanding of climate change impacts on SCL operations. | Emphasis and support within the utility and city for the importance of considering climate change adaptation in utility operations. | $100,000 per year for 2013 and 2014 | A City Light climate preparedness strategy is under development which will identify additional actions which may require additional funding. | SCL will provide information on climate change impacts and adaptation actions to customers as needed. | On Track. Two research studies funded to study the impacts of glacial recession and snowpack loss on streanflow for hydropower geenration and fish protection.
A8 | Maximize conservation programs to help meet future electricity needs, reduce the need for new energy sources as Seattle grows, reduce energy costs to residents and businesses, and help meet obligations for natural resource stewardship. |  | SCL |  | Achieve 14.0 aMW energy conservation per SCL Strategic Plan. | Achieve 14.0 aMW energy conservation per SCL Strategic Plan. | Conservation targets are reassessed through periodic updates to the Seattle City Light Strategic Plan and Integrated Resource Plan (IRP). | $43.3 million | None | Outreach through strategic planning and IRP processes; outreach and marketing to customers for participation in conservation programs. | Completed. Ongoing- Seattle City Light remains committed to achieving 14 aMW of conservation-related energy savings, to supporting customer renewables and to maintaining its greenhouse gas neutrality.
A9 | Implement advanced metering to begin the transition to a "smart grid" to help meet customer demand, detect system overloads tht could be caused by heat events or other issues, and reroute power to improve system reliability. |  | SCL |  | Hire project manager, establish project team, hire expert educational consultant, develop workforce development plan for impacted employees. | Adopt health and privacy policies, develop business case and submit BIP, develop and issue RFP for implementation. | Decision to proceed with implementation. | Strategic Plan includes placeholder for funding from 2015-2018. | Strategic Plan includes placeholder for funding from 2015-2018. | Community forums, outreach to businesses and organizations, website, surveys, info sheets/FAQs, e-bulletins, DON liaisons. | On track.
A10 | Work with federal and academic research groups to downscale climate data for the watersheds supplying the city's water. Use this information to update the water supply assessment and explore impacts on the intensity of forest fires, turbidity, the timing of fall rains, and precipitation in the city. |  | SPU | SCL | Obtaining downscaled date, generating climate-altered hydrology, running hydrology through operational and system models to assess impacts; also exploring impacts on fire intensity in watersheds, return of fall rains. | Continue impacts assessment, evaluate adaptation options. | None | 2013-2014: $140,000 | None | TBD; will definitely present at water sector events | On track.
A11 | Continue to invest in water conservation programs reducing per capita water use to help meet future needs and to build adaptive capacity. |  | SPU | SCL Parks | implement regional program per Actions and Strategies report (http://savingwater.org/docs/2013WaterConsProgActionsStrategies.pdf). Implement Seattle Low-income Water Conservation Assistance Program. | Same as 2013 | SPU CIP and Operating budget | $2 million for Regional Water Conservation; $650,000 for low-income water conservation assistance. | None | Various for programs identified in Actions and Strateiges. | On track.
A12 | Continue to evaluate the impact of climate change on the drainage system and identify strategies for enhancing resilience. |  | SPU |  | Initiate Drainage and Wastewater Climate Resilience Study examining what combination of SLR and rainfall causes problems in our system. For tidally-influenced basins. | 2013 activity will extend into 2014; planning to include non tidally-influenced basins as well. | None | 100000 | $60,000 to add non tidally incluenced basins, but may be able to fund with 2014 budget. | None at this point | On track.
A13 | Adopt a Green Stormwater Infrastructure (GSI) policy and implementation strategy affirming GSI as the preferred stormwater management approach. |  | OSE (with SPU) | SPU, SDOT, Parks | Policy adopted in March 2013 via Executive Order and in July 2013 via City Council Resolution. | Implementation Strategy will be drafted in Q3-4, 2013 and in Q1-Q2, 2014. | No policy changes are needed to support the development of the Implementation Strategy. Policy changes may be needed to support delivery of the Implementation Strategy . | Development of Implementation Strategy will be achieved within existing resouces. | Delivery of Implementation Strategy will require new resources. Possible budget alternatives will be outlined in the Strategy. | A public comment period following the release of the DRAFT Implementation Strategy is anticipated for early Q2, 2014. | On Track. The Implementation Strategy is slated to be released for public comment at end of the first quarter of 2015.
A14 | Expand precipitation monitoring and evaluation capabilities to mitigate future urban flooding risk and enhance understanding of neighborhood-scale climate impacts. |  | SPU |  | Expand use of social media. | Enhancements to Seattle RainWatch system. Expansion and enhancement of SPU rain gage network. | None | Staff resources | None | Social media, conferences, publications | On track.
A15 | Evaluate the impacts of sea level rise on flood prone areas and shoreline development and habitat, and consider implications for land use management strategies. |  | SPU & DPD |  | Updating and publication of citywide sea level rise maps. Addition of minor sea level rise provisions to the Stormwater Code. | Initiate Drainage and Wastewater Climate Resilience Study examining what combination of SLR and rainfall causes problems in our system. For tidally-influenced basins only. Consideration of ECA and SMP revisions. | None at this point | 60000 | TBD | TBD | On track.
A16 | Pilot an advanced green building standard on a City facility, such as the Living Building Challenge (LBC), to assess its appropriateness for resilient design and to promote similar levels of green building in the private market. |  | OSE | TBD | Identify capital projects with potential to pursue LBC and engage with project teams. | Assessment of future building projects relevant for LBC. Continued engagement with Capital Depts. and project teams. | Direction from City leadership for a capital Dept. to pursue LBC. | Staff resources | TBD - There could be incremental design and construction costs above standard Multiple Awards Construction Contract (MACC). | None | Not Initiated. OSE has been working with departments to identify an approporiate project. A project was not identified in 2014; however, we are pursuing several promising leads.
A17 | Review development codes and incentives and identify barriers and opportunities to encourage private development to become more resilient. |  | DPD | OSE, SPU | An implementation strategy for this action will be developed as part of the citywide climate adaptation strategy in 2014. | [5 empty] | On track.
A18 | Continue to factor climate change projections into emergency preparedness and recovery planning, including future updates to the Seattle disaster readiness and rsponse Plan and the Disaster Recovery Plan. |  | OEM | SCL, SPU, SDOT, OSE, DOIT, OED and others | Update to the Seattle Hazard Identification and Vulnerability Analysis (SHIVA). | Climate change will be considered as we develop the Disaster Recovery Plan and update the Disaster Mitigation Plan | None | This work will be covered by funding already identified for the Disaster Recovery Plan and the Mitigation Plan Update. | None | Several workshops with stakeholders and community members. | On track.
A19 | Strengthen the local and regional food system by impelmenting the Seattle Food Action Plan and consider the impacts of climate change on access to healthy, affordable food in future plan updates. |  | OSE | DON, HSD, OED, SDOT, DPD, DPR, SPU | 1. Continue to support and implement all actions identified in the Food Action Plan. 2. Expand Fresh Bucks to all Seattle farmers markets. 3. Pilot a program to lease City-owned land to urban farmers. 4.Adopt healthy vending guidelines for machines on City property. 5. Expand the Farm to Table program. 6. Integrate policies supportive of healthy food access and urban agriculture into Seattle plans. 7. Identify obstacles to the viability of Seattle farmers markets, and recommendations to address those obstacles. | 1. Explore opportunities for Seattle to protect regional farmland. 2. Explore the need for infrastructure (i.e. processing, cold storage, aggregation) that will help get more produce from regional farmers into the City of Seattle market. 3. Explore opportunites to reduce preventable food waste. 4. Identify new opportunities to improve food access for people with low-income, low food access, people of color, and immigrant communities. | None | All of the departments listed have roles in implementing the Food Action Plan, and have various amounts budgeted for implementation. The 2014 Proposed Budget includes $100,000 for the Fresh Bucks program and $136,000 for the Farm to Table program. | OSE and the Food IDT will be identifying budget needs for implementation of the food action plan. Additional resources will be needed for full implementation. Some elements have resources budgeted, but will require additional funds to fully implement. | The public was engaged during the development of the food action plan. OSE is working with the Food IDT to evaluate the need for additional public engagement as we move toward plan implementation, particularly in historically underrepresented communities. | On track.
A20 | Expand community gardening and urban agriculture opportunities at P-patches, schools, and on rooftops and inventory vacant land that could be made available for farming. |  | DON | OSE, Parks, SDOT, OH | Add seven community gardens including leadership development programs to support equity goals and self-management of the garden. | Add three community gardens including leadership development programs to support equity goals and self-management of the garden. | None | Supported by Parks & Open Space Levy ($2.5 million) | None | Direct community outreach with volunteers and staff, listservs, signs. The program uses multi-lingual outreach workers as appropriate. | Partially Completed. In 2013 P-Patch added five gardens in communities throughout Seattle including BitterLake, Magnolia, New Hollly, Rainier vista and Highland Park , providing garden space for 180 families. In 2014, P-Patch added three gardens, in Northwest, Capitol Hill and Beacon Hill providing garden space for 106 families.
A21 | Continue efforts to preserve farmland near the city through land use and Transfer of Development Rights (TDR) policies. |  | DPD |  | The Council passed legislation implementing a regional TDR program for South Lake Union and Downtown. | Implementation and monitoring of regional TDR program. | None | Staff resources | None | Community outreach during development of program and media outreach about passage. | Completed. Development projects have begun to take advantage of the program.

## Council Priority Actions
Council Priority Actions
Action | Lead staff | Lead Dept | Implementation Status | Update
Develop a comprehensive climate impacts preparedness strategy. |  | OSE | On Track. | An interdepartmental team is assessing the vulnerabilities and risk of future climate conditions to City operations and services, and planning actions to help enhance resilience. Equity is a critical focus of the planning effort and early in the 2015 the team will participate in climate justice training and planning to help build capacity to effectively incorporate equity goals into the planning process.
Work with regional and state partners to adopt a funding strategy to meet current and future transportation funding needs. |  | SDOT | On Track. | PSRC is forming a TPB subcommittee to develop a potential regional transportation funding alternative, in case the state legislature does not act on transportation funding. CM O’Brien will be on the subcommittee. In addition, the Mayor has been asked to take part in the Transportation Futures Task Force, which will look at long-range transportation funding and policy issues at the state and regional level.
Develop a citywide transit communities strategy including creation of equitable development policies. |  | DPD | On Track. | Major work being conducted to update City's Comprehensive Plan. Increased emphasis in Plan on equity and equitable development. Draft EIS currently being prepared to assess impacts on communities of color that could result from increased development around frequent transit. Draft Plan to be issued in July and Final in December.
Develop and begin implementation of a coordinated land use & transportation plan in a high priority transit and bicycle cooridor. |  | DPD & SDOT | On Track. | For the 23rd Avenue corridor SDOT and DPD have continued coordinated community engagement by sharing meetings and also by sending out shared meeting notices. The coordinated planning between SDOT and DPD improved both the urban design framework for the 23rd/Union, 23rd/Cherry, and 23rd/Jackson nodes and the 23rd Avenue corridor transportation design. Knowledge of the urban design issues at the 3 nodes (Union, Cherry, Jackson) allowed for the 23rd Ave plan to include elements to help improve these nodes. 23rd will remain an important transit corridor, and through the design a parallel neighborhood greenway will be constructed on 22nd Avenue.
Research the benefits of pricing policies on climate protection, transportation, and community goals and their potential social equity impacts. |  | SDOT | On Track. | SDOT is hiring a consultant to complete the work by the second quarter of 2015.
Include health, safety, and equity outcomes in transportation & land use planning building on the Healthy Living Assessment. |  | DPD & SDOT | On Track. | DPD and SDOT are working jointly on coordinated projects in the Rainier Valley (Rainier Beach and Mt. Baker) and Ballard that include health, safety, and equity focuses such as equitable TOD, healthy food, and safe access to transit.
Consider a transportation modal hierarchy as part of the 2015 Comprehensive Plan upate in order to assess greenhouse gas reductions, safety, mobility and funding priorities. |  | DPD & SDOT | On Track. | SDOT is developing a modal decision making framework, rather than a strict modal hierarchy, that provides policy supported direction to making difficult mode decisions in the limited right-of-way.
Transition Community Power Works Home program to an established program. |  | OSE | Completed | In 2013, OSE selected a non-profit to manage day-to-day operations of the CPW Home program in partnership with SCL, and completed a business plan for 2014-2015. In spring-summer of 2014, final implementation contracts were signed and "CPW 2.0" fully launched under the daily management of Clean Energy Works.
Expand district energy systems on First Hill and into the South Lake Union & Denny Triangle neighborhoods. |  | OSE | On Track. | First Hill: Corix (district energy utility) screening study was completed in December, 2013. Next steps are awaiting King County decisions on hospital heating systems. South Lake Union & Denny Triangle: Corix has completed a business case study and is proceeding to establish a customer base and obtain a City permit to build the needed infrastructure in the right-of-way.
Pilot a utility incentive program that would pay for actual energy savings over time instead of providing up-front payment for projected savings. |  | SCL | On Track. | The Conservation Resources Division initated the Pay-for-Performance Program in early-2013 with three commercial office buildings. Data from the first full year of operation is being compiled and a third party has been recently hired to review the energy savings claimed by the program participants. This pilot program is a three-year effort and will conclude in mid-2016.
Require buildings undergoing major renovations or change of use to come close to the energy performance requirements for new buildings. |  | DPD | Completed | This requirement was adopted in the 2012 Energy Code update as a requirement that all "substantial alterations" to commercial buildings comply with the current energy code.
Develop and test a program for rating and disclosing home energy performance. |  | OSE | On Track. | Early research and stakeholder engagement was conducted in 2014. Primary outreach and policy development are planned for 2015.
Note on F6: ONeillK2: